## Sheet1
Sr.No. | Task | ETA (Hr) | Challenges | Status
1 | Proper 2D Asset Import-Sprites/Audio/Images/Buttons etc. | 3 |  | Done
2 | UI-StartUpUI / LobbyUI / MainGameUI /PauseUI/GameoverUI | 4 |  | Done
3 | Core Snake Game Functionality:- 1.Snake Movement on keyboard Input 2.snake should die after colliding own collider | 4 |  | WIP
4 | 2.Power-Ups 1.Shield → Snake will have a shield and the snake will not die when the shield is active. 2.Score Boost → Snake will gain 2x Score Points for each mass-gainer food. 3.Speed Up → Snake should increase the speed after collecting this power-up. powerUps Spawning | 4 |  | Done
5 | Foods Mass Gainer → Which will increase the length of sneak. Mass Burner → Which will decrease the length of sneak. Food spawning | 5 | Increse/ Decrese Logic | Done
6 | Scoring Mass Gainer Food will increase the score. Mass Burner food will decrease the Score. | 3 |  | Done
7 | Co-Op Here comes spice ©️ Malhar's Game Design 😎 Implement a two-player game where one sneak will move using WASD and another will move using arrow keys. ⬆️ ⬇️ ⬅️➡️ If Snake A bites snake B then snake B will die, and vice versa. | 9 | Multiple challenge | WIP
8
9
10